## Sheet1
Requirement ID | Description of Requirement | Story Points | Priority | Sprint No.
1 | Set up Unity Environment | 1 | 1 | 1
2 | Obtain/Set up Equipment | 1 | 1 | 1
3 | Connect VR hand movement | 3 | 2 | 2
4 | Connect VR head movement | 5 | 2 | 2
5 | Code player movement | 8 | 2 | 2
6 | Learn Blendr tutorial | 3 | 3 | 2
7 | Import/Design chair | 5 | 3 | 3
8 | Import/Design desk | 5 | 3 | 3
9 | Import/Design whiteboard | 8 | 4 | 3
10 | Import/Design marker | 8 | 4 | 3
11 | Chair physics | 8 | 5 | 4
12 | Marker physics | 13 | 6 | 4
13 | Whiteboard physics | 13 | 7 | 4
14 | Multiplayer connection | 8 | 8 | 5
15 | Voice chat | 8 | 12 | 5
16 | Text chat | 5 | 20 | 5
17 | User Menu | 5 | 30 | 6
18 | Finish School Design | 13 | 33 | 6
19 | Settings | 8 | 35 | 6
20 | Mute Capabilities | 5 | 35 | 6
21 | Kick Capabilities | 3 | 35 | 6
22 | Character Customization | 13 | 40 | 7
23 | Additional classrooms | 13 | 45 | 7
24 | Lobby | 13 | 50 | 7
25 | Compatibility for all VR | 8 | 55 | 7