## Sheet1
Requirement ID | Description of Requirement | Story Points | Priority | Sprint No.
1 | Set up Unity Environment | 1 | 1 | 1
2 | Obtain/Set up Equipment | 1 | 1 | 1
3 | Connect VR interactions | 2 | 1 | 2
4 | Design Chairs and Desks | 3 | 2 | 2
5 | Design Whiteboard/Marker | 3 | 2 | 2
6 | Chair physics | 5 | 2 | 3
7 | Desk physics | 5 | 3 | 3
8 | Whiteboard physics | 13 | 4 | 4
9 | Marker physics | 8 | 4 | 5
10 | Multiplayer connection | 13 | 4 | 5
11 | Voice Chat | 8 | 6 | 6
12 | Text Chat | 8 | 7 | 6
13 | Mute Capabilities | 5 | 8 | 6
14 | Kick Capabilities | 5 | 12 | 6
15 | Finish School Design | 8 | 20 | 7
16 | User Menu | 5 | 30 | 7
17 | Character Customization | 13 | 33 | 7
18 | Lobby | 13 | 35 | 7
19 | Settings | 5 | 35 | 7
20 | Compatibility for all VR | 3 | 35 | 7
21 | Server Optimization | 13 | 40 | 7
22 | Additional classrooms | 13 | 45 | 7